## Readme
BENTHIC IMAGERY ACTION PLAN TRACKER
Version: | 1.7
Last updated: | 2023-08-16
Prepared by: | Plan Development Group of the Big Picture Benthic Imagery Analysis Workshop (March 2019)
PDG members (Mar19-Mar20): | Henk van Rein | Joint Nature Conservation Committee | Lead
| Alison Benson | Envision Mapping Ltd | Environmental consultancy representative
| Charlie Lindenbaum | Natural Resources Wales | Inshore SNCB imagery representative
| Hayley Hinchen | Joint Nature Conservation Committee | Offshore SNCB imagery representative
| Jen Durden | National Oceanography Centre | Academic research representative
| Jon Hawes | Centre for Environment, Fisheries and Aquaculture Science | Government research representative
| Phil Boulcott | Marine Scotland Science | Government research representative
About the Benthic Imagery Action Plan Tracker: The Benthic Imagery Action Plan provides a strategic framework to carry out necessary improvements to a wide range of imagery analysis standards in the UK. Under the governance of the North-East Atlantic Marine Biological Analytical Quality Control Scheme (NMBAQC) of the Healthy and Biologically Diverse Seas Evidence Group (HBDSEG), the Action Plan lays out a ‘road map’ for the UK to follow that will encompass current needs for improvement as well as those expected to emerge with increasing use of new technologies. A key purpose of the Action Plan is to streamline the improvements into coherent work flows, so that national resources are used more efficiently. There will also be greater opportunities for knowledge exchange and collaborative working via the Action Plan. This spreadsheet, the 'Action Plan Tracker', provides a means of recording progress towards tasks and as a tool to enable better planning between organisations interested in carrying out tasks from the Action Plan. A static copy is published on the NMBAQC website and a 'live' copy is maintained by the Action Plan Coordinator of the Big Picture Group.
SPREADSHEET CONTENTS:
1. Action Plan Tracker tab (APT):
| ACTION PLAN TASK INFORMATION | Theme | General working theme of the task
|  | Proposed Project Working Group | Aggregations of linkged tasks into proposed working groups to be tackled as a project
|  | Task no. | Unique ID of the task
|  | Task | This is a list of the tasks (projects/actions/ideas) provided by participants at the Big Picture Workshop that are required to progress benthic imagery analysis standards and working practices across the UK
|  | Proposed way of working | The likely approach need to carry out the task: Action, Coordination, Project, Multiple projects, Workshop
|  | Suggested deliverable/s | The intended result/deliverable/output from the task
|  | Priority | All tasks have a composite prioritisation score to indicate the relative importance of the task in the Action Plan. This is calculated by adding the following factors together: 1. the total number of connections each task has to others (both within its theme and outside), e.g. 8 connections; 2. the hierarchical/procedural order/level of the task within each theme, with earlier tasks appearing higher in the flowcharts and scoring more than lower tasks that would depend more on completion of the higher order tasks (scale varies across themes depending task hierarchies but max scale is 1-8), e.g. 5 levels up from bottom of theme; 3. the relative urgency and importance of task as recommended by Big Picture Workshop participants and Plan Development Group, scored on a 1-10 scale with 10 representing immediate need, e.g. task urgency score 8. When these scores are added together they are sorted into scales to represent their relative priority in this Action Plan. The composite scores, scale ranges and recommended actions are listed here:
|  |  | High priority (H) | Moderate priority (M) | Low priority (L)
|  |  | Scores >15 | Scores 10-15 | Scores 1-9
|  |  | Must be prioritised in first phase of Action Plan, for immediate action as soon as projects can be set up. Alternatively, these tasks must form the key aims of projects connected to this Action Plan | These are the majority of tasks in this Action Plan and tend to underpin the success of many of the High Priority tasks. They should be accompany the High Priority tasks in most projects but not be the focus of the project | Important tasks that are not critical to the success of the Action Plan but nonetheless represent important work areas that should be completed when they can be. Could be factored into projects to bring additional value
|  | Task status | The status of the task. Can be "Complete", "On-going", "Under consideration" or "Hasn't started"
| TASK OUTPUTS | Output link (weblink to download files) | A weblink to a site where key task outputs can be accessed and downloaded
| TASK DEVELOPMENT | Task leads (current/future interest) | Organisations that are currently leading work on this task, perhaps in a project, and/or organisations with an interest in being a lead partner in taking this task forward in future. They would be expected to organise a project team, lead project development and management, as well as seek funding for the work
|  | Task collaborators/team (current/future interest) | Organisations that are currently working within a wider team in this task area but not leading the task. This column is also for organisations to express their interest in working in a team in which they are expected to contribute to the delivery of future tasks but not to lead them
|  | Task steering group (current/future interest) | Organisations that currently review and steer progress on a task or are interested in doing so for a future task. They are not expected to work on or lead a task but rather their committment is to provide advice and guidance on how the task could be best delivered
|  | Task funding source (current/suggested) | Current or potential future funding sources for the task
|  | Project name | The name of the project in which the task is to be delivered
| ADDITIONAL TASK INFORMATION | Current work in task area | Existing relevant progress and current work in this task that could contribute to the delivery of the task
|  | Notes for task | Additional notes relevant to this task
2. Action Plan Tracker - Proposed Project Working Groups (APT-PWG) |  |  | A summary table from Tab 2 to show a reorganisation of tasks into the proposed Project Working Groups alongside the tasks and expressions of interest in working on the tasks.
3. Big Picture Group tab: lists organisations that are involved in the NMBAQC Big Picture Group
VERSION CONTROL
Version | Date | Notes | Author | Distribution
0.1 | 2019-09-13 | Initial version created using notes Big Picture workshop | Henk van Rein | To PDG
1 | 2020-03-27 | First 'live' Action Plan Tracker for NMBAQC | Henk van Rein | Big Picture Group; NMBAQC website
1.1 | 2020-09-02 | Initial expression of interest for sharing at BPG webinar 8 Sept 2020 | Henk van Rein | BPG
1.2 | 06/20/20 | Collation of interest in Tasks from BPG | Henk van Rein | BPG
1.3 | 2020-11-25 | Addition of proposed Project Working Groups | Henk van Rein | BPG Teams site and Active members
1.4 | 2021-10-15 | Action Plan Coordination Committee Meeting | James Albrecht | BPG
1.5 |  |  |  | BPG
1.6 | 2022-11-29 | Aditional information added to each task from BIAP pdf document | James Albrecht | BPG
1.7 | 2023-08-16 |  | James Albrecht | updated on NMBAQC website

## APT
ACTION PLAN TASK INFORMATION | [8 empty] | TASK OUTPUTS | TASK DEVELOPMENT |  |  |  |  | ADDITIONAL TASK INFORMATION
Theme | Proposed Project Working Group | Task no. | Task | Additional information about task | Proposed way of working | Suggested deliverable/s | Priority | Task status | Output link (weblink to download files) | Task leads (current/future interest) | Task collaborators/team (current/future interest) | Task steering group (current/future interest) | Task funding source (current/suggested) | Project name | Current work in task area | Notes for task
Governance & co-ordination | Benthic Imagery Action Plan co-ordination | 1 | Embed Action Plan in suitable governance structure (HBDSEG) | HBDSEG or one of its sub-groups, e.g. NMBAQC, are an ideal group to champion and report progress of the Action Plan to. They represent all the marine biodiversity conservation interests for the UK Marine Monitoring and Assessment Strategy (UKMMAS). | PDG working | HBDSEG Benthic Imagery Action Plan | H | Complete | periodic snashots published on NMBAQC website: http://www.nmbaqcs.org/scheme-components/epibiota/benthic-imagery-action-plan/ | JNCC | Cefas, NOC, Envision Ltd, NRW, MSS | The Big Picture Group | Defra | Defra Marine Methodologies
Governance & co-ordination | Benthic Imagery Action Plan co-ordination | 2 | Create an Action Plan managing body and systems for coordinating projects across UK | A central managing body/coordinator to record and report progress of Action Plan tasks, and to liaise with users of the Action Plan. | Group coordination | HBDSEG Benthic Imagery Action Plan Coordinator | H | Complete |  | JNCC, NMBAQC | SEPA, Envision, UoP, Cefas, NRW, MBA, NOC, IFCA | Envision |  |  | the Action Plan coordination committee has been set up and consists of PWG leads, representatives from Academia, Government, and the commercial sector | The Action Plan Coordination Committee (APCC) is a quarterly/periodic meeting with Project Working Group leads and additional members. This is a central place to report on progress from tasks in the action plan. The meetings are lengthly, hard to justify cost. How can we fund attendance by different groups, such as consultancies? Are there other ways we can engage that are more time effective? We could send out a doodle poll to determine how consultancies would like to stay engaged? We could have short focus groups or hour long engagement groups?
Governance & co-ordination | Benthic Imagery Action Plan co-ordination | 3 | Explore range of options and decide on optimum approaches for publishing and sharing new research findings, standards and recommendations for the working group |  | Coordination | Recommended information sharing routes for imagery work | L | In progress |  | Big Picture group | [5 empty] | When you publish something on Teams, do you email everyone in the Big Picture mailing list? A notification is needed to make it clear when new documents are published (not everyone can access the Teams channel, not everyone receives notification etc). The group's work needs to be disseminated more widely. Items on this list are consensus and discussion based and can't really be delegated. We often miss detail on the background of the tasks, and go over the same ones again. The BIAP is currently the central place to find information, but it is not obvious where to find this. Need to consider options and if there is a better way to share information.
Governance & co-ordination | Benthic Imagery Action Plan co-ordination | 4 | Create working group file-sharing and collaboration site | File sharing site and communications platform already set up for Big Picture Group using Microsoft Teams could be good start point to develop this task. Site must develop according to the needs of the Action Plan and Big Picture Group. | Lead action | File-sharing and collaboration site for Big Picture Group | M | On-going |  | JNCC |  | The Big Picture Group | Defra | Defra Marine Methodologies | JNCC have been trialling a collaboration site on Microsoft Teams since July 2019. This works well as a place to host files that everyone can access. I have not seen it being used much for collaboration | Other options under consideration are Huddle and Slack. SEPA would be very keen on this idea.
Governance & co-ordination | All projects | 5 | Explore imagery cost models for standard development, research, training and data dissemination | Understanding of current imagery related costs needed, as well as potential funding sources. Development of potential cost models to fund all stages of benthic imagery workflows in future, e.g. centrally funded by Competent Monitoring Authorities (CMAs) and government or funded by commissioning organisation? Exploration of suitability and viability of different costs models, as well as group wide consideration of modes for implementation. | Coordination/ Review | Options for imagery cost models for standards development | H | Under consideration |  |  | JNCC |  |  |  |  | Context behind this relates to funding opportunities - some pots of funding available to certain topics or groups, we need a way to fund other topics. Steering group were tasked with finding and assessing funding opportunities and sharing these with working groups. Funding isssues related to staff time
Governance & co-ordination | Quality Assurance Framework for benthic imagery | 6 | Develop contract management guidelines for benthic imagery analysis work in UK | Understanding of current imagery related costs needed, The quality of benthic imagery products, as well as the relationship between contractors and clients, can be improved by general contract management guidance for benthic imagery analysis work carried out in the UK. The guidance could include as a check lists for all parties to follow. Must include work in the following areas: • Improve clarity of specification in image analysis contracts to improve quality of products, efficiency and promote realistic tenders; • Include aspects of conflict of interest and issues of timing guidelines (for analysis) in specifications; • Consider how to improve two-way communication throughout image analysis contracts, as well as embedding formal feedback sessions (review of initial subset of data, or a ‘wash up’), at regular intervals throughout contracts; • Provide more information to contractors on purposes/objectives of survey and sampling design to improve understanding and accuracy of tendering; • Consider how to improve the quality of imagery and metadata let out in image analysis contracts, including removal of poor-quality imagery beforehand; • Add an initial familiarisation phase to each image analysis contract to review data and improve learning opportunities pre-annotation; • Add options to share all data after a contract or not: ‘opt in or opt out’ clause; • Implement recording of annotation metadata, i.e. analysis methods, annotation approach, analysts, training level, accreditation, analyst variability.as well as potential funding sources. Development of potential cost models to fund all stages of benthic imagery workflows in future, e.g. centrally funded by Competent Monitoring Authorities (CMAs) and government or funded by commissioning organisation? Exploration of suitability and viability of different costs models, as well as group wide consideration of modes for implementation. | Lead action | Improved imagery analysis contract specifications | M | Under consideration |  |  | JNCC, NE, Cefas | NS, SEPA, Seastar Survey Ltd. |  |  | NS - have stills analysis guideline examples | Task supported by CMA/SNCBs Marine Scotland would like to be considered to work on this - lots of ideas! Statutory Nature Conservation Bodies (SNCBs) would also be interested in these outputs. Guidance documents could be versioned (with links to other documents that are updated) and sent to contractors, as imagery analysis is developing quickly.
Governance & co-ordination | Benthic imagery data flows | 7 | Review imagery data culture in UK and explore possible incentives to share imagery data | Literature reviews, questionnaires and interviews to understand data sharing culture of different organisations in UK. Explore barriers to data sharing, e.g. industry/academia/government could be credited (good publicity rewards) or free advertising opportunities created to raise positive profile of organisations or organisations could pay reduced subscription fees to save costs. | Coordination/ Review | Range of options for incentives for sharing of imagery data across UK | L | Hasn't started |  |  | JNCC, Gardline, Envision | Gardline, SEPA, Seastar Survey Ltd. | Crowd Funding Source |  |  | Task supported by CMA/SNCBs Different organisations, working groups etc. have different cultures - the task is to self reflect on this (e.g. on the uptake of science and best practises). Needs to be considered at different levels e.g. committee, working groups etc. Consider discussing this during the in-person workshop, and allowing people to input virtually.
Governance & co-ordination | Benthic Imagery Action Plan co-ordination | 8 | Discuss imagery standard requirements with Department of Business, Energy and Industrial Strategy (BEIS) | This task aims to improve communication and to build a positive relationship between the regulators of offshore industry activities (BEIS) and the marine biodiversity conservation community of the UK. Develop mutually beneficial targets for the future. | Coordination | BEIS collaboration for standard setting | L | Hasn't started |  |  | Gardline, NE | Gardline, Cefas |  |  | Task may fit in a different project working group - Data Flows | This task aims to improve communication and build a positive relationship between the regulators of offshore industries (BEIS) and the marine biodiversity conservation community of the UK. Develop mutually beneficial targets for the future. SEPA - BEIS? - They don’t set British standards
Governance & co-ordination | Benthic Imagery Action Plan co-ordination | 9 | Identify taxonomic experts for all taxonomic groups | This group likely exists in different forms so may simply involve contacting existing groups. Important to determine which of the experts would be willing to be contacted for identification queries, training and other Action Plan work. | Group action and coordination | List of benthic taxonomic experts | M | In progress |  | JNCC | Kerry Howell (UoP), Emma Sheehan (UoP), Jaime Davies (UoP), Tammy Horton (NOC) | Gardline |  |  | there are probably existing lists of taxonomic experts, but there is a task to contact taxonomic experts to see if they are willing to be contacted (any list would have to be GDPR compliant). There is also an existing list of WoRMS editors (https://www.marinespecies.org/aphia.php?p=editors). Progress being made on this through the SMARTAR-ID project- huge task and resource constraints.Need to identify more taxonomists, likely through WoRMs. | The Big Picture Group could collectively create this list SEPA - MASTS? Needs a combination of taxonomists and parataxonomists - works best when both are in the same room and understand eachothers needs. Difficult to find taxonomists, and those that understand our issues.
Governance & co-ordination | Benthic Imagery Action Plan co-ordination | 10 | Create image analysis training body and governance structure to manage training materials and potentially carry out a range of courses/refreshers and publicise workshops | The NMBAQC are a logical starting point for this group. The future group must have sustainable cost model for operation as a training body, including consideration of training funds/subsidies for participants. Must engage with universities, museums, consultancies, international taxonomists. | Coordination | Imagery training body | L | Hasn't started |  |  | Kerry Howell (UoP), Emma Sheehan (UoP), SEPA, Jaime Davies (UoP), Seastar Survey Ltd., Cefas, Nicola Foster (UoP) | Gardline, Envision |  |  | there is a list of Literature and Taxonomic keys for epibiota available through NMBAQC (https://www.nmbaqcs.org/scheme-components/epibiota/literature-and-taxonomic-keys/) | Shouldn’t this be the NMBAQC? SEPA - Shouldn’t NMBAQC lead this? Could this be linked to MASTS for longer-term training and scholarships for new experts? Task could fit in Machine learning working group? Originally here as this task applied more to the guidance that others apply
Governance & co-ordination | Benthic Imagery Action Plan co-ordination | 11 | Create a machine learning and annotation user ‘group’ for the UK | This group likely exists in different groups so task would need to connect with those groups initially. Additional call of interest for organisations interested in image annotation and machine learning to identify a pool of experts to build supportive, collaborative community across stakeholders. Consider expanding groups membership to international organisations would have additional benefits of expertise and access to new resources. | Coordination | Machine learning and imagery annotation user group | M | Hasn't started |  |  | JNCC, Kerry Howell (UoP), Gardline, Emma Sheehan (UoP), SEPA, NE, Cefas, Nicola Foster (UoP) | Gardline, EA |  |  |  | Potentially split this into separate ML and annotation SEPA - MASTS? Task could fit in Machine learning working group? Originally here as this task applied more to the guidance that others apply
Overarching guidelines and purposes for imagery | Quality Assurance Framework for benthic imagery | 12 | Identify and define range of main purposes for using benthic imagery | JNCC started work on this task – questionnaire sent out to Big Picture Group to determine uses/purposes of benthic imagery, how it is acquired, why it used, how it is processed and what products are produced. | Project | Defined range of standard purposes for using benthic imagery | H | Complete |  | JNCC | The Big Picture Group via questionnaires and interviews | The Big Picture Group, MEDIN | Defra | Defra Marine Methodologies; Development of a Epibiota QA system for NMBAQC | Complete – available through the NMBAQC website through the Quality Assurance Framework Guidance: https://www.nmbaqcs.org/scheme-components/epibiota/epibiota-quality-assurance-framework-and-documents/ Includes a flow chart diagram developed from interviews with members of the group to collect info on different ways in which people were using imagery. Addressed this task by recording info in proformas, enabling us to collect data to MEDIN standards. Because the Big Picture has paired itself with NMBAQC, this may constrain the purposes of imagery. The proformas have been developed to comply with minimum standards, i.e. MEDIN. However, there is room to develop these proformas further. If MEDIN changes their standards, we may need to go back and review this.
Overarching guidelines and purposes for imagery | Quality Assurance Framework for benthic imagery | 13 | Identify standard requirements for grouped main purposes and create standard table and decision tree flowchart | Purposes grouped by similarity to represent core purposes - imagery products/outputs must form the basis of each core purpose. Core purposes structured into hierarchy of minimum standard for all imagery, general level (mapping) and then specific level (monitoring). Decision-tree flowchart produced to help users identify their purposes. Cost of implementing each purpose must be considered. Core purposes will be used to develop basic minimum standards for data outputs and working practices in future. | Project | Core purposes for using benthic imagery and minimum requirements for each purpose | H | Complete |  | JNCC | The Big Picture Group via questionnaires and interviews | The Big Picture Group, MEDIN | Defra | Defra Marine Methodologies; Development of a Epibiota QA system for NMBAQC | Complete – available through the NMBAQC website through the Quality Assurance Framework Guidance: https://www.nmbaqcs.org/scheme-components/epibiota/epibiota-quality-assurance-framework-and-documents/ Needs to be a discussion about whether we should stay tied with NMBAQC? The ways NMBAQC operate may not always work best for imagery.
Overarching guidelines and purposes for imagery | Benthic imagery workflow guidance | 14 | Guidance for entire imagery analysis work flow (design, analysis, randomisation, annotation, statistics), including decision tree flowchart | Guidance for entire work flow, including design, analysis/annotation design (preparation to extract/annotate), statistical tests, implementation of standards to randomise the order of all imagery to be analysed to reduce learning effects on data. Guidance must convey importance of each stage in entire work flow being connected and interdependent (from acquisition to annotation/analysis to reporting). | Action | Annotation order of imagery randomised in procedures | H | In progress |  |  | JNCC, Kerry Howell (UoP), Emma Sheehan (UoP), SEPA, Jaime Davies (UoP), Envision, Jen Durden (NOC), Brian Bett (NOC), NE, Cefas | Gardline, Envision |  |  | Cefas - flow charts and toolboxes have been created to provide guidelines for the entire process within Cefas (CICCAM). Cefas have been progressing this task. All current work has been piecemeal, and limited solely to the direct requirements of BaU analysis and reporting activity that Cefas are involved in (including the Biodiversity monitoring partnerships with JNCC / NE / EA). It is hoped that a write up to draw together progress made and current status of elements of task 14 (noting limitation to only current delivery not full scope of Big Picture group & imagery needs and purposes) will be together by ~Feb/March ’23. CICAM Delivery Action Plan diagram shows the different stages of the imagery analysis life cycle from collection to stats. Cefas are planning to make the guidance available to the Big Picture Group early next year. This will provide an opportunity to give feedback on the workflow, test it, and compare it with existing work flows. Actions are bound in MPA reports, need to collate these together into a useable document i.e. to apply to future survey designs, planning etc. Any other working flows being used? Natural Resource Wales now use simple Standard Operating Procedures (SOPs) – these are specific to each project. Could consider all of these together, and develop overarching guidelines. Marine Scotland will also be working on developing work flows. | Could be supported by NMBAQC and MEDIN regarding data flows and standards
Overarching guidelines and purposes for imagery | Benthic imagery workflow guidance | 15 | Develop guidance on determining appropriate sampling units from imagery data sets, including aggregation criteria (e.g. randomness) to meet minimum sample size recommendations for different purposes and targets | Assignment of standard, minimum, sample sizes for different purposes and targets based on defining the sampling population under investigation and determining the number of individuals needed within each sampling unit. Guidance must also include table for recording aims of each study and what the sampling population (spatial scale/size) is. Summary flow chart to cover steps needed to define sampling units, aggregate data and determine correct number of replicates needed. Provide numerous examples of different survey scenarios for context. Provide clear terminology. | Project | Sampling unit guidance | M | In progress |  |  | JNCC, Kerry Howell (UoP), Emma Sheehan (UoP), SEPA, Jaime Davies (UoP), Jen Durden (NOC), Brian Bett (NOC), PMSL, NE, Cefas | Gardline |  |  | Task considered in task 14 (Entire imagery analysis workflow) above. National Oceanography Centre (NOC) is working on this – the point of the task is to transfer work of quantitative working groups (e.g. on samples sizes) into this workflow. NOC has a funded project, and is working on this now (see detail below). NOC has just written a standard for defining the sampling population - the paper is in review, and it is being added into the iFDO standard. NOC has a funded project to work on the technical aspects of sampling unit size for early 2023. The sampling population work is applicable to all purposes. The sample unit size definition will be for individual-based work, and cover most spatial/monitoring purposes. Once this is done, it will need to be considered/translated to make it appropriate for this group/contracts. Working group lead needs to make clearer (in the BIAP, diagrams etc) that this task follows on from work of other groups (i.e. by mapping connections between tasks) | Should link to guidelines in Task 18
Overarching guidelines and purposes for imagery | Benthic imagery workflow guidance | 16 | Alignment of imagery acquisition parameters with minimum sample size recommendations and sample selection criteria for each core purpose | Recommendations produced for each core purpose. Task targeted at improving technical aspects of imagery acquisition by better aligning image resolution constraints, ground resolution specification, image size/video length considerations, quality constraints, random selection criteria (e.g. randomness of samples for data aggregation) during sampling. | Multiple projects | Acquisition practices aligned with sample size and selection recommendations | H | Hasn't started |  |  | JNCC, Kerry Howell (UoP), Emma Sheehan (UoP), Jaime Davies (UoP), PMSL, NE, Cefas | Gardline, SEPA, Envision |  |  | Cefas / JNCC - OOVR & OBRG / GHF surveys and analyses from a monitoring or mapping point of view. Keen to contribute to this from monitoring work, but assuming guidance itself will be under NMBAQC.Task considered in task 14 (Entire imagery analysis workflow) above. Need to go back to working group and consider how they would like to take this task forward. This task is included in work flows developed by Cefas, mentioned above. This is a huge task as depends on so many parameters e.g. water quality, resolution etc. outputs from Task 15 fit into this task. The technical content depends on outputs from other working groups. Important to consider technological advances. May be difficult to standardise and compare new and old datasets. A good place to start, would be recording what everyone does now. Others as part of other initiatives are working on this – could use their outputs. Also important to consider standardising the imagery analysis.
Overarching guidelines and purposes for imagery | Quality Assurance Framework for benthic imagery | 17 | Develop minimum data standards for imagery core purposes | Consider the most appropriate levels that an analysis needs to reach for each purpose. Could use MEDIN data ingestion standards to develop standards for each core purpose (this would make all data collected under each purpose compliant with MEDIN). However, data standards must be cost effective and sustainable to be implemented so task will need to consider this aspect too. | Multiple projects | Imagery data output standards for standard purposes | H | In progress |  | JNCC, NE | Kerry Howell (UoP), Emma Sheehan (UoP), Jaime Davies (UoP), MEDIN, Cefas | Gardline, SEPA, Envision | Defra | Development of a Epibiota QA system for NMBAQC | MEDIN compliant proformas have been developed to MEDIN standards and are available on the NMBAQC website for the different imagery purposes identified: https://www.nmbaqcs.org/scheme-components/epibiota/epibiota-quality-assurance-framework-and-documents/. This progresses but does not complete this task. Some of this task has been completed by developing Ifdo MEDIN standards – not yet implemented. The task developed from questions from a previous workshop on how much time people should spend annotating imagery and whether imagery should be analysed for future purposes, as well as for the individual project. The task is about analysing images collectively, and how they can be standardised to be used for other purposes in future. Important to consider consistency between projects. Funding also a consideration. Could consider a two level decision tree in guidance, i.e. on what is needed, and what is desirable (i.e. if funding allows). Important to develop this guidance for contractors, to benefit future reporting. This should be simple and consistent. Consider should imagery be analysed for points, polygons, % cover? Should only a subset be analysed? Important to have thorough metadata for futureproofing. Important task for JNCC, NRW and other SNCBs in terms of their reporting obligations. | MEDIN proformas and BIIGLE data outputs (JNCC) useful
Overarching guidelines and purposes for imagery | Benthic imagery workflow guidance | 18 | Develop minimum requirements for acquisition that meets the needs of each common purpose, to include assurance that minimum sample sizes are attained for each purpose | Requirements produced for each purpose. Task targeted at developing guidelines for minimum imagery acquisition requirements for each purpose, that meet the data output requirements, with incorporated quality assurance measures. | Multiple projects | Minimum acquisition standards for standard purposes | M | In progress |  |  | NE, Cefas | JNCC, Gardline, SEPA, Envision |  |  | Cefas- working on this topic as part of ongoing MPA work and CICCAM. Keen to lead the research on this, but assuming requirments themselves will be under NMBAQC. Task considered in task 14 (Entire imagery analysis workflow) above. | Should build on existing NMBAQC guidelines, linking up with Task 15
Overarching guidelines and purposes for imagery | Quality Assurance Framework for benthic imagery | 19 | Develop minimum standards for data quality and apply to in-house and contracted analyses, including time and budget estimates in contract specifications | Task involves developing data quality standards that can be quickly applied to raw imagery data sets to ensure they are fit for purpose, i.e. they are fit for annotation, further analysis and data storage later on. | Coordination | Data quality standards for in-house and contractual analyses | H | In progress |  | NE | JNCC, EA, NE, Cefas | SEPA, MEDIN, Seastar Survey Ltd. |  |  | This task is at the end of the flow diagram, and relies on other tasks (including task 14) above. Marine Scotland keen to engage with this task - relates to task 6 in the Governance and co-ordination theme.
Acquisition of imagery | Benthic imagery workflow guidance | 20 | Develop short guidance for minimum suitable conditions for imagery acquisition on surveys | This task provides guidance on suitability of survey conditions during the acquisition of the imagery. It should cover what conditions are optimum for imagery acquisition, i.e. to improve quality of data and what limits could be placed on suitability of conditions at sea as well as water clarity issues. Guidance must consider inshore/offshore survey differences. | Project | Minimum suitable conditions for imagery acquisition on survey | M | Hasn't started |  | NE | SEPA, Envision, Eastern IFCA, Seastar Survey Ltd., EA, PMSL, Cefas | JNCC, Gardline, SEPA, Envision, Eastern IFCA, EA |  |  | Eastern IFCA have experience in the use of acquisition, processing and use of visual imagery for the management of MPAs. We especially have experience of low cost, rapid, practical pragmatic assessments, and work in low visibility dynamic environments.
Acquisition of imagery | Benthic imagery workflow guidance | 21 | Develop 'live' methods for assessment of initial image quality while on survey | A ‘live’ assessment of the quality of raw imagery on survey could reduce cost and efforts later on by enabling users to filter out poor quality imagery early on in data flows. This can have implications for image analysis contracts, especially if poor quality imagery can be removed early on. | Project | Enhanced on-survey QA and QC of imagery | M | In progress |  | Cefas | SEPA, Eastern IFCA, Jen Durden (NOC), Seastar Survey Ltd., PMSL | JNCC, Gardline, Eastern IFCA, EA |  |  | SEPA - Looking at suggested guidelines for checking the quality of data in the field. Eastern IFCA have experience in the use of acquisition, processing and use of visual imagery for the management of MPAs. We especially have experience of low cost, rapid, practical pragmatic assessments, and work in low visibility dynamic environments. Cefas - CICCAM imagery standardisation/ selection toolbox
Acquisition of imagery | Benthic imagery technology reviews | 22 | Review capabilities, requirements and limitations of different video formats (HD-4K-8K) | This much needed review should aim to forecast future scenarios where still imagery is extracted from frame grabs taken from video. The review must weigh up costs, benefits and limitations of different video formats and make recommendations regarding suitability of video format for extracting still images. | Literature review and recommendations | Future capabilities of video | L | Hasn't started |  |  | SEPA, Envision, Eastern IFCA, Seastar Survey Ltd., PMSL, Cefas | JNCC, Gardline, Eastern IFCA, EA |  |  | SEPA - developed requirements for what video formats and quality we will accept | SEPA - this is something that could be contracted out as a project (CREW, MASTS?).
Acquisition of imagery | Benthic imagery technology reviews | 23 | Review use of low-cost camera systems for acquisition of benthic imagery | Low-cost camera systems are widely used in shallower water (e.g. Go-Pro). Aspects of their usage, costs, benefits and limitations should be reviewed to produce recommendations for their optimum use. | Literature review and recommendations | Low-cost camera system recommendations | M | In progress |  | NE, Cefas | JNCC; DAERA MCRT, Kerry Howell (UoP), Emma Sheehan (UoP), Envision, Eastern IFCA, PMSL | Eastern IFCA, EA |  |  | NS - we havent done a literature review but have looked into different options SEPA - as above. Eastern IFCA have experience in the use of acquisition, processing and use of visual imagery for the management of MPAs. We especially have experience of low cost, rapid, practical pragmatic assessments, and work in low visibility dynamic environments. Cefas - we have designed and tested (to 60m) a micro ROTV system which is hand deployable. | SEPA - this is something that could be contracted out as a project (CREW, MASTS?).
Acquisition of imagery | Benthic imagery technology reviews | 24 | Review of laser-profiling techniques for different purposes | This review should explore practical applications and uses for this technology and develop recommendations accordingly. | Literature review and recommendations | Laser profiling recommendations | L | Hasn't started |  |  | Envision, Eastern IFCA, PMSL, NE | JNCC, Eastern IFCA, EA |  |  |  | SEPA - would the UK Seabed mapping group not been interested in this one?
Acquisition of imagery | Benthic imagery technology reviews | 25 | Review citizen science approaches for using benthic imagery and develop recommendations for future approaches | There is massive potential in the use of citizen science approaches for benthic imagery work, especially with the collection of recreational diver imagery or crowd-sourced image annotation of large data sets. This important review must collate examples of existing approaches, evaluate their effectiveness and consider where these existing approaches, or new ones, may be suitable for future benthic imagery work. | Literature review and recommendations | Citizen science recommendations | M | Hasn't started |  | NE | DAERA MCRT, Jen Durden (NOC), NE, Cefas | NS, Eastern IFCA |  |  | NS- currently developing something similar | SEPA - is this not Seasearch methods?
Acquisition of imagery | Benthic imagery technology reviews | 26 | Diver based methods review | A long overdue review of the range of diver-based imagery acquisition approaches, their costs, benefits and limitations. Review has potential to recommend the optimum approaches for using diver-based imagery for the future. | Literature review and recommendations | Guidelines for diver imagery acquisition regarding wafting | M | Hasn't started |  | NE |  | Eastern IFCA |  |  | Eastern IFCA have some experience of working with volunteer divers | Could be carried out via Interagency Marine Monitoring Group. SEPA - is this the MNCR methods (Phase 1) or the MCS Seasearch methods?
Acquisition of imagery | Benthic imagery technology reviews | 27 | Review of ancillary equipment usage and provide recommendations on best practice | This review is more relevant to large camera systems that increasingly have ancillary equipment (lasers, sensors for pressure, temperature, conductivity, turbidity, chlorophyll, light) attached to the camera frame. This review should identify the uses of this equipment and the range of situations in which it is useful. It would be useful to consider the implications of use of this equipment on smaller camera systems too. | Literature review and recommendations | Best-practice recommendations on use of ancillary equipment | M | Hasn't started |  | Cefas | Eastern IFCA, Seastar Survey Ltd., PMSL, NE | JNCC, Gardline, Envision, Eastern IFCA, EA |  |  | Eastern IFCA have experience in the use of acquisition, processing and use of visual imagery for the management of MPAs. We especially have experience of low cost, rapid, practical pragmatic assessments, and work in low visibility dynamic environments. | SEPA - this is something that could be contracted out as a project (CREW, MASTS?).
Acquisition of imagery | Benthic imagery technology reviews | 28 | Review of environmental data acquisition and usage, and provide recommendations on best practice | A review of different environmental parameters determined directly from imagery, e.g. sediment composition, habitat, and indirectly by ancillary equipment attached to the camera frame, e.g. temperature, salinity, turbidity, chlorophyll. Recommend best-practice for the acquisition of this data, to also include some analysis recommendations. | Literature review and recommendations | Best-practice recommendations on environmental data acquisition | M | Hasn't started |  |  | NS, Eastern IFCA, PMSL, NE, Cefas | JNCC, Gardline, Eastern IFCA, Seastar Survey Ltd., EA |  |  | NS - currently looking into expanding the Scottish coastal observatories and increased environmental (mainly physical) monitoring alongside ongoing biological. Have been in contact with staff at Skomer MNR for advice. Eastern IFCA have experience in the use of acquisition, processing and use of visual imagery for the management of MPAs. We especially have experience of low cost, rapid, practical pragmatic assessments, and work in low visibility dynamic environments. | SEPA - this is something that could be contracted out as a project (CREW, MASTS?).
Acquisition of imagery | Benthic imagery technology reviews | 29 | Review potential uses of photogrammetry to meet different purposes and determine requirements of imagery to be acquired – apply to case study | Review of the technology, current and potential applications, costs, benefits and limitations, to provide recommendations for future application for different purposes. Consider carrying out a case study. | Literature review and recommendations | Photogrammetry recommendations | L | Hasn't started |  | NE | Envision, Eastern IFCA | Gardline, Envision, Eastern IFCA |  |  |  | SEPA - this is something that could be contracted out as a project (CREW, MASTS?).
Acquisition of imagery | Benthic imagery technology reviews | 30 | Review potential uses of video mosaicing to meet different purposes and determine requirements of imagery to be acquired – apply to case study | Review of the technology, current and potential applications, costs, benefits and limitations, to provide recommendations for future application for different purposes. Consider carrying out a case study. | Literature review and recommendations | Video mosaicing recommendations | L | Hasn't started |  | NE | Envision, Eastern IFCA, PMSL | Gardline, Envision, Eastern IFCA |  |  |  | SEPA - this is something that could be contracted out as a project (CREW, MASTS?).
Acquisition of imagery | All projects | 31 | Periodically update existing guidance on acquisition and analysis of imagery to reflect new developments, and produce new guidelines where necessary | This general task is represented in three themes and related to the need to update guidance on benthic imagery acquisition and analysis periodically so that the most up-to-date approaches are being used. Guidance should include specific quality assurance measures, such as training, as well as quality control checks for data, and perhaps also variability assessments (habitats and analysts). It is anticipated the exact focus of guidance from this task will be informed by user needs. Current interests expressed around Drop Down Video and SCUBA diver guidance suggest updates in these areas are a high priority. | Group action | Periodic reviews of procedures | H | Hasn't started |  |  | Eastern IFCA, PMSL, NE, Cefas | Gardline, Envision, Eastern IFCA, EA |  |  | Eastern IFCA have experience in the use of acquisition, processing and use of visual imagery for the management of MPAs. We especially have experience of low cost, rapid, practical pragmatic assessments, and work in low visibility dynamic environments. | General task applicable to all guidelines, that they should be kept reasonably up to date.
Acquisition of imagery | Benthic Imagery Action Plan co-ordination | 32 | Contact developers of imagery acquisition systems to learn about what they are developing and, potentially, influence future developments | Develop communications and build relationships with developers of imagery acquisition systems to influence future developments. | Group action | Developer involvement in benthic imagery work | L | Under consideration |  | Cefas | NE | Gardline, Eastern IFCA, EA |  |  | Cefas - have contacted several developers of newq and innovative imagery technology in past 18 months
Acquisition of imagery | Intercallibration Table Project | 33 | Develop intercalibration tables for different data acquisition systems, where value and benefit are possible | Assessment of data acquisition systems and potential for intercalibration of data outputs. This task aims to enhance the accessibility of imagery data sets where value and benefit of using intercalibration tables can be demonstrated. | Project | Intercalibration tables for acquisition equipment | L | Hasn't started |  |  | NE? | Eastern IFCA, EA |  |  | Eastern IFCA have experience in the use of acquisition, processing and use of visual imagery for the management of MPAs. We especially have experience of low cost, rapid, practical pragmatic assessments, and work in low visibility dynamic environments.
Imagery annotation approaches | Identification approaches for benthic imagery | 34 | Review taxonomic identification approaches for benthic imagery | This task may be best carried out with the assistance of a questionnaire sent out to the Big Picture group. | Project | Review of identification approaches | H | Hasn't started |  |  | JNCC, Kerry Howell (UoP), Gardline, Emma Sheehan (UoP), SEPA, Jaime Davies (UoP), Tammy Horton (NOC), Seastar Survey Ltd., PMSL, NE, Cefas, Nicola Foster (UoP) | Gardline
Imagery annotation approaches | Identification approaches for benthic imagery | 35 | Develop guidance on minimum sizes of organisms that should be counted, e.g. 10mm in 1m2 | Guidelines on the minimum size of taxa that can be accurately identified from different types of benthic imagery, including different levels of image resolution, ground resolution, image quality, stills vs video. | Project | Minimum taxa size guidelines for enumeration | M | Under consideration |  |  | JNCC, Gardline, Emma Sheehan (UoP), SEPA, Brian Bett (NOC), Seastar Survey Ltd., NE, Cefas, Nicola Foster (UoP) | Gardline | Defra | Development of a Epibiota QA system for NMBAQC
Imagery annotation approaches | Identification approaches for benthic imagery | 36 | Explore whether taxonomic identification should only be carried out for certain taxa groups that an analyst is confident to annotate | Comparison of different taxonomic identification scenarios in which all taxa in an image are identified by every analyst and where a limited list of taxa are analysed by each analyst. Each analyst must demonstrate expertise in identification of the taxa on their limited list. Guidelines could be produced from the results to promote taxonomic identification strategies that maximise efficiency and data quality. | Project | Taxonomic identification guidelines | M | On-going |  | JNCC | Gardline, SEPA, Jaime Davies (UoP), Tammy Horton (NOC), Seastar Survey Ltd., NE, Cefas | Gardline, EA | Defra | Development of a Epibiota QA system for NMBAQC
Imagery annotation approaches | Identification approaches for benthic imagery | 37 | Develop Epifauna Identification Protocol (EIP) to improve consistency of taxonomic nomenclature | The NMBAQC have started work on this with the support of the JNCC. This existing work must provide a starting point for this task. Urgent need for more consistency in taxonomic identification standards for imagery annotation. List of expert taxonomists expected to be consulted to develop the EIP. | Project | Epifauna Identification Protocol | H | On-going | http://www.nmbaqcs.org/scheme-components/epibiota/epibiota-quality-assurance-framework-and-documents/ | JNCC | Kerry Howell (UoP), Gardline, Emma Sheehan (UoP), SEPA, Jaime Davies (UoP), Tammy Horton (NOC), Seastar Survey Ltd., PMSL, NE, Cefas | Gardline | Defra | Development of a Epibiota QA system for NMBAQC | Workshops to increase taxa included in EIP during 21/22 FY | EIP first published in 2020. ongoing work to further develop EIP in FY 21/22
Imagery annotation approaches | Identification approaches for benthic imagery | 38 | Review morphological classification systems and recommend optimum approaches for future | Review existing of morphological systems to include advantages and disadvantages of systems such as CATAMI10, Morphological Taxonomic Unit (MTU) catalogue, deep-sea morphologies11 and Sponge Morphologies (Bell and Barnes, 2001). | Project | Review of morphological classification systems | H | Under consideration |  |  | JNCC, Kerry Howell (UoP), Emma Sheehan (UoP), Jaime Davies (UoP), Envision, NE, Cefas, Nicola Foster (UoP) | JNCC, Gardline, Envision, EA | Defra | Development of a Epibiota QA system for NMBAQC
Imagery annotation approaches | Identification approaches for benthic imagery | 39 | Create standardised UK-based morphology-based system (e.g. CATAMI) for use on benthic imagery, including biotope monitoring | Work has started on this task between Cefas and JNCC but will require significant additional input from datasets across the UK to develop a CATAMI-style morphological classification system. | Project | Morphology-based classification system for epifauna in UK | H | On-going |  | JNCC | Kerry Howell (UoP), Gardline, Emma Sheehan (UoP), Jaime Davies (UoP), Envision, PMSL, NE, Cefas, Nicola Foster (UoP) | Gardline, Envision, EA | Defra | Development of a Epibiota QA system for NMBAQC
Imagery annotation approaches | Identification approaches for benthic imagery | 40 | Carry out pilot test to explore combined use of morphology-based classification system (e.g. CATAMI) and Epifauna Identification Protocol (EIP) | Application of UK morphological classification system alongside EIP should first be trialled to assess efficiency and quality of this combined approach. It could also be trialled using image annotation software for additional benefits. This pilot test aims to produce guidelines to recommend next steps. | Project | Taxonomic and morphological identification guidelines | M | In progress |  | Cefas | JNCC, Kerry Howell (UoP), Gardline, Emma Sheehan (UoP), Jaime Davies (UoP), Nicola Foster (UoP) | Gardline | Defra | Development of a Epibiota QA system for NMBAQC | Cefas - OOVR, OBRG, WTBF
Imagery annotation approaches | Identification approaches for benthic imagery | 41 | Explore possibility of using a staged approach to object identification to improve efficiency and data quality | Using existing guidance, trial different annotation approaches to optimise efficiency and data quality, e.g. identify physical features first, then morphological (e.g. CATAMI), then genus and species (if possible). | Project | Taxonomic and morphological identification guidelines | M | Hasn't started |  |  | NE | Gardline
Imagery annotation approaches | Identification approaches for benthic imagery | 42 | Consider development of standard checklists of taxa/morpho-groups for surveys | Using existing guidance, trial the effect of having standards list with a reduced number of taxa/morpho-groups for annotators to use on survey to improve efficiency and data quality. If successful, trial use of develop a standard approach for making and using the taxa/morpho-group checklists | Project | Reduced taxa/morpho-groups lists for surveys | M | Hasn't started |  |  | DAERA MCRT & MMAT | Gardline, NE
Imagery annotation approaches | Identification approaches for benthic imagery | 43 | Recommend minimum requirements for taxonomic and morphological identification to meet different benthic imagery purposes | Review and evaluate existing approaches to taxonomic and morphological feature identification, and develop guidelines for minimum requirements for what taxa and morpho-groups must be identifiable from imagery for different benthic imagery purposes. | Multiple projects | Minimum identification guidelines for standard purposes | M | Hasn't started |  |  | DAERA MCRT & MMAT, Tammy Horton (NOC) | Gardline, Seastar Survey Ltd., NE |  |  | SEPA - have suggested a minimum JNCC habitat classification level we expect operators to identify to.
Imagery annotation approaches | Enumeration approaches for benthic imagery taxa | 44 | Review enumeration approaches, including SACFOR, for benthic imagery | Review of enumeration approaches to evaluate their costs, benefits and limitations. Range of approaches could be better understood using a questionnaire to Big Picture Group. | Project | Enumeration method review | H | Under consideration |  |  | Jaime Davies (UoP), Envision, Brian Bett (NOC), Jen Durden (NOC), Seastar Survey Ltd., PMSL, NE, Cefas | JNCC; NS, Envision |  |  |  | SEPA - MASTS project?
Imagery annotation approaches | Enumeration approaches for benthic imagery taxa | 45 | Publish JNCC enumeration comparison method study | This study has been completed and will be published by JNCC by end of December 2019. | Project | Enumeration method comparison report | H | Complete | https://hub.jncc.gov.uk/assets/3dbf346b-685c-4db1-90a1-b205af482146 | JNCC | ASML, Envision Ltd | JNCC | Defra | Defra Marine Methodologies
Imagery annotation approaches | Enumeration approaches for benthic imagery taxa | 46 | Explore ways to improve the consistency of records made by enumeration techniques | Test and trial different enumeration approaches to maximise consistency of data recorded by different human analysts. Computer annotation may also be explored in this task as algorithms may yield more consistent results by annotating benthic imagery data sets. | Project | Consistency recommendations | H | Hasn't started |  |  | Jaime Davies (UoP), Envision, Jen Durden (NOC), NE | Envision |  |  |  | SEPA - MASTS project?
Imagery annotation approaches | Enumeration approaches for benthic imagery taxa | 47 | Decide on future uses of SACFOR | Review uses of SACFOR and results from method comparison studies to understand best use of SACFOR in future. Perhaps retained as intercalibration or mapping tool for next 5 years? | Action | SACFOR recommendations | M | Under consideration |  |  | Jaime Davies (UoP), NE | NS |  |  |  | SEPA - MASTS Project?
Imagery annotation approaches | Enumeration approaches for benthic imagery taxa | 48 | Develop the minimum requirements for enumeration approaches to suit different benthic imagery purposes | Optimum enumeration approaches can be developed for taxa and morph-groups to suit each benthic imagery purpose, to benefit data quality, improve efficiency and enhance data sharing opportunities across UK. Approaches should align to different resourcing scenarios and needs of the purpose. | Multiple projects | Minimum enumeration guidelines for standard purposes | M | Hasn't started |  |  | NE, Cefas
Imagery annotation approaches | Enumeration approaches for benthic imagery taxa | 49 | Create a decision-tree to support selection of enumeration approaches for different purposes and resourcing scenarios | Create flowchart to help users select the ideal enumeration approach for their resources and purposes. | Project | Minimum enumeration guidelines flowchart for standard purposes | L | Hasn't started |  |  | Jaime Davies (UoP), Envision, NE, Cefas | Envision
Imagery annotation approaches | All projects | 50 | Assessment of data metrics (accuracy, precision, consistency, efficiency) from different image annotation strategies (software vs traditional), to include aspects of working on large collections of imagery | Comparison studies of different annotation strategies exploring the costs and benefits of using traditional human- based data recording vs annotation software used by humans. Study could also explore use of annotation software used by machines (machine-learning). Important to use large data sets for comparisons to highlight current and future needs. | Project | Optimisation of annotation software approaches vs traditional approaches | M | Hasn't started |  |  | Brian Bett (NOC), Jen Durden (NOC), NE, Cefas | EA
Image annotation software and machine learning | Imagery annotation software | 51 | Explore potential addition of metadata tags to imagery, including taxonomic and morphological classification, location, depth, temperature | Trial application and develop use of various metadata tags/labels for benthic imagery. Should include location tags of taxa/morpho-groups (to create location-based taxa lists in future) and ancillary sensor data if possible: depth, temperature, turbidity etc. | Project | Addition of metadata tags to imagery | H | Hasn't started |  |  | JNCC, SEPA, Jaime Davies (UoP), Brian Bett (NOC), PMSL, NE | MEDIN |  |  |  | Epifaunal Identification protocol is not mentioned here but provides that label tree with a standard way of labelling things. Problem is it does not take morphological classification into account. IFDO standard - the data work flows Working Group will be looking into this more and CATAMI. Extension to IFDO is being worked on by Jen Durden ready early April 2023. Metadata tags, outcome was that easier to do in excel. Location depth and temp don't need to be annotated on to image, can be put into excel spreadsheet, big advantage is being able to share a label tree. Combining morphology and taxonomy into one label tree is tricky but some mentioned using nested systems. Speed is the essence for this task, so need to determine if quicker doing in BIIGLE or Excel. Useful links: https://www.nespmarine.edu.au/document/catami-classification-scheme-scoring-marine-biota-and-substrata-underwater-imageryhttps://github.com/catami/classification https://github.com/catami/classification https://www.nmbaqcs.org/scheme-components/epibiota/epibiota-quality-assurance-framework-and-documents/
Image annotation software and machine learning | Imagery annotation software | 52 | Define features that software platforms must have for annotation and machine learning | Software features of importance to machine learning applications. | Project | Requirements of annotation and machine learning platforms | H | Under consideration |  | Cefas | Gardline, Nils Piechaud (NOC) | Gardline, EA |  |  | Cefas happy to lead, but this will require significant input from non-govermental parties wit field- specific reccomendations | Some issues with access to BIIGlE in some organisations, which impacts the software is used. Others could share their experience to support others here.
Image annotation software and machine learning | Imagery annotation software | 53 | Implement recording of annotation metadata, i.e. analysis methods, annotation approach, analysts, training level, accreditation, analyst variability | Trial application and develop use of annotation metadata tags/labels for benthic imagery. Should include tags/labels of analysis methods, annotation approach, analysts, training level, accreditation, analyst variability, all of use for data sharing. | Action | Annotation metadata recorded in procedures | H | On-going |  |  | SEPA, Jen Durden (NOC), Nils Piechaud (NOC) | JNCC | NMBAQC? MEDIN? |  | GEOMAR and BIIGLE have been working on a standard for image annotations called iFDO - https://marine-imaging.com/fair/ifdos/iFDO-overview/ | Tasks focus around increasing awareness of the different annotation tools. Not prescribing one tool but benefits in commonality. Suggested task : Members to develop Pros and cons lists of the different platforms they use. Questionaire. Another task to communicate with BIIGLE and other platform developers to add features that are needed.
Image annotation software and machine learning | Imagery annotation software | 54 | Integrate recommended enumeration and identification approaches with image annotation software | This milestone task combines the optimum annotation theory and approaches with annotation software to produce high- quality digitally annotated imagery and data. | Action | Optimum identification and enumeration approaches used with annotation software (Milestone moment) | H | Under consideration |  |  | SEPA, Envision, Cefas | JNCC, Envision |  |  | Cefas have lead the use of BIIGLE annotation and a (published) protocol is under constant review as new projects futher our understanding of what is needed for MPA imagery analysis. | This task should be adopted by all imagery users wherever possible
Image annotation software and machine learning | Machine-learning approaches for benthic imagery | 55 | Define data format specifications necessary for machine learning algorithms to work, as well as export formats for biologists to use (e.g. csv files) | Consult with leading developers to determine their data format specifications (import/export) of machine learning algorithms. | Project | Data format requirements for machine learning algorithms | H | Hasn't started |  | Kerry Howell (UoP) | Kerry Howell (UoP), Gardline, Nils Piechaud (NOC) | Gardline | NERC |  | Kerry working on AI Algorithms, data from BIIGLE to Yolo, BIIGLE already exports in CoCo format. Will be part of BIIGLE manual to be released before Xmas, then people are asked to input their requirements. Project run by Ifremer that is developing the translation tools between different annotation tools and from annotation software into a particular software.
Image annotation software and machine learning | Machine-learning approaches for benthic imagery | 56 | Review image annotation software and machine learning approaches for benthic imagery analysis purposes to explore differences in user interface, open-source vs contracted, point vs polygon/boxes, stills vs video | Numerous review likely exist to provide this task with a head- start. Search AUV community research for current software. Explore all ensemble approaches (multiple models can learn from each other). | Project | Review of current annotation and machine learning approaches | H | Hasn't started |  | Kerry Howell (UoP) | Kerry Howell (UoP), Gardline, Jaime Davies (UoP), Jen Durden (NOC), Nils Piechaud (NOC), Brian Bett (NOC), NE, Cefas | Gardline | NERC |  | Not going to be done - it does not matter which annotation software you use. More to do here as questions are: What can we use AI to do? What should we use AI to do? How should you approach you annotation to make it future proof. Links to what we want to use this information for, which links to guidance group. General rules are needed for how to annotate. Data have to be in a certain format for machine learning. Standards are needed but importantly scripts and tools needed to transform that data format. | Task 56 could this be added to survey for task 52 - what features do people find useful, which are not.
Image annotation software and machine learning | Benthic imagery data archives and catalogues | 57 | Create a pathway for annotated imagery to be shared with machine learning community (via common image library?) | Data flows need to be understood and sources of annotated imagery discovered. Pathways to machine learning community must be able to cope with hundreds of thousands of images for train algorithms (estimated 100K images needed of different taxa and morpho-groups). | Project | Open access to imagery library (for machine learning algorithms) | H | Under consideration |  |  | Gardline, Nils Piechaud (NOC) | Gardline |  |  | Project run by Ifremer that is developing the translation tools between different annotation tools and from annotation software into a particular software. Fathom net is a pathway to share information. inaturalist is another but not quite similar. Data work flow working group - DASH, MEDIN, BDOC also looking at this - images and annotations linked together. | Organisational permission to make data available is still an issue here,
Image annotation software and machine learning | Machine-learning approaches for benthic imagery | 58 | Carry out a machine learning workshop for key participants in UK machine learning community (biologists and computer engineers) to conceptualise works flows for benthic biology imagery and facilitate collaboration |  | Workshop | Machine learning workshop for benthic ecologists | M | Hasn't started |  | Kerry Howell (UoP) | NS, Kerry Howell (UoP), Gardline, Emma Sheehan (UoP), SEPA, Envision, PMSL | Gardline, EA |  |  | Workshop - still needed - limitation that can only be done for the workflow we are following. Cefas also doing work here. Kerry thinking of linking to Challenger to deliver. | Should a contract be let to cover quite a few of these machine learning elements - bit of a lit review and organise a workshop? If there is a workshop, could this then provide training material for others who do not attend workshop. Links to 76.
Image annotation software and machine learning | Machine-learning approaches for benthic imagery | 59 | Scope out international expertise in machine learning and explore options for how to collaborate | Seek our expertise in machine learning to collaborate in UK projects where possible. | Coordination | List of international contacts with expertise in machine learning using benthic imagery | M | On-going |  |  | Jen Durden (NOC) |  |  |  | This is happening, Jen and Kerry linked to international groups,
Image annotation software and machine learning | Machine-learning approaches for benthic imagery | 60 | Define targets/tasks for machine learning algorithms to be tested on, such as identifying indicator taxa in benthic imagery | Targets may be specific taxa, morph-groups, communities, biotopes, habitats or substrata. Must be relevant to scope of Action Plan. May consider open competitions within machine learning community to stimulate development of specific tools to detect targets (requires funding/rewards for prizes). | Project | List of targets/tasks for machine learning algorithms | H | Hasn't started |  |  | Nils Piechaud (NOC), NE | Gardline |  |  | No progress but could be a survey, as people using it for different purposes. Survey BP community. Could use previous survey that was done. Need to think about the questions are to gather info about a large scale questions rather than individual level. | Links to purposes - so what the person is interested in getting out of it. Scope set by Governance group, there maybe things that are not covered by each group individual purpose. creating a matrix/decision tree could potentially be useful. It could be based on what the goal(s) of a project the user has and they would answer questions and based on that the user would receive suggested targets/tasks. Perhaps allow for the user to adjust the suggestion to be more general or specific as needed for the work. Number 14 also has decision trees. so 60 would feed into 14
Image annotation software and machine learning | Machine-learning approaches for benthic imagery | 61 | Explore potential uses and value of image annotation and machine learning approaches to support Quality Assurance procedures, training, development of reference collections |  | Project | Role of annotation and machine learning approaches in QA | M | Hasn't started |  | Cefas | SEPA, Jen Durden (NOC) | Gardline, Envision |  |  | Cefas developing a script that others can use here. Jen Dueden supervises a PhD working on coral cover looking at quality control, variability between annotators. Australian team looking at clustering of imagery to help prioritise what you annotate. The distributing you images across the variability in the data set, to make sure you capture that variability in the pre-processing.
Image annotation software and machine learning | Machine-learning approaches for benthic imagery | 62 | Explore use of google imagery to substitute machine learning needs |  | Project | Use of google images for machine learning applications | M | Hasn't started | [6 empty] | No plans. Jen and Kerry feel this task is not needed by wider group, it also will not age well. Over prescribing rather than looking at general process. So is it more about general sources to enhance your machine learning? Fathom net is an available source on this. Task to be redefined as open source rather than google.
Image annotation software and machine learning | Machine-learning approaches for benthic imagery | 63 | Develop confidence assessment approaches for machine learning outputs | Confidence assessment will likely be verified by human annotators, perhaps expert taxonomists in the target taxa/group. These assessments should become standard for all machine learning outputs in the scope of this Action Plan. | Project | Machine learning confidence assessments | L | Hasn't started |  |  | Kerry Howell (UoP), Jen Durden (NOC) | Gardline |  |  | Jen D working on this to look at how you evaluate your AI outputs in terms of the ecology. Action to build best practices document on how to do this, which will be shared on ocean best practices website.
Data flows | Benthic imagery data flows | 64 | Consider what data should be shared and how it could be archived | Consider full range of data generated from benthic imagery and the potential value and benefits of sharing that data. Important to understand data culture of different organisations and incentives for sharing data. | Project | Data archive flows | M | On-going |  |  | DAERA MCRT? Kerry Howell (UoP), MBA/DASSH, Emma Sheehan (UoP) | JNCC, Eastern IFCA, NE? |  |  | Training aspects of this task have been completed. Graeme and Dan have looked at ways of sharing video, through discussions with Montery Bay Aquarium who have similar issues. There is not formal working group at present but there is an ambition for one. Most work is progressed currently through other groups. This theme is related to others and needs sharpening up. Other groups will need steers on definition of terms. People are unclear on what data means in this context. Needs improving and specifying in the table. Work needs to keep aligned with evolution of standards. | DASSH
Data flows | Benthic imagery data flows | 65 | Identify current data-sharing flows and gaps for benthic imagery | Flows should be mapped out and costs/benefits/limitations evaluated. JNCC Marine Monitoring Platform Guidelines data flow diagram could be a good start point for this task. May also require a questionnaire to Big Picture Group to understand every organisations unique data flows. | Project | Understanding current data-sharing flows and gaps | M | Under consideration |  |  | Kerry Howell (UoP), MBA/DASSH, Emma Sheehan (UoP), Jaime Davies (UoP) | JNCC; NS, Eastern IFCA, NE? |  |  | Some work ongoing through other initiatives. BIODIG have done some work on data sharing, but this misses the academic and private sector, more work is needed. Recommended routes have been progressed through DASH (https://www.dassh.ac.uk/maims/) providing an archive for imagery. This system links annotated data through to MEDIN guideline, keeping the link between standard, annotation and image together. This is a pilot study for images only, not videos at present. Discussion on organisations having their own catalogues but brought together into one front end. Federated idea - aim to support to each other. Infrastructure and hosting videos are very challenging due to costs. JNCC do not share video for same reason. Cefas have no catalogue but wonder if they could set one up using similar systems that federates the others. Some of tasks 65 and 66 will be explored in NOC Digital Twin project. | BIODIG?
Data flows | Benthic imagery data flows | 66 | Target data-sharing gaps for imagery, explore potential data-sharing options products and recommend routes for organisations to follow in order to make their data available | This task relates to the potential of re-purposing imagery, i.e. adding value to imagery that has already been collected and used once before. Likely sharing-routes between WoRMS, OBIS, Pangaea, Marine Recorder, DASSH, MEDIN. Important to understand data culture of different organisations and incentives for sharing data. | Project | Options and recommendations to address data sharing gaps | M | On-going |  |  | Kerry Howell (UoP), MBA/DASSH, Emma Sheehan (UoP) | NS, Eastern IFCA, NE? |  |  | Action for the group to make a recommendation for Cefas and other groups about what system is needed for them setting up a new system. System could be linked with current catalogues. However linking all catalogues is still under consideration (IIIF - https://iiif.io/).
Data flows | Benthic imagery data archives and catalogues | 67 | Develop online common image library/catalogue to collate and share reference collections across the UK | Reference collections generated following NMBAQC guidelines can be used as a feedback mechanism to improve consistency of future identification. Imagery library could collate existing reference collection imagery from organisations and be expanded to include other potential libraries and existing resources including MEDIN, DASSH, Habitas, NOAA, FathomNet12 (MBARI), JNCC imagery library; National Oceanography Centre (NOC), Cefas, Marine Scotland Science). Can draw on experiences of sharing reference collections from ICES Working Group on Nephrops norvegicus (Nephrops) Surveys (WGNEPS). Set up quality assurance and quality control processes for incoming imagery using experts, including assignment of confidence scores. Library could link to WoRMS database via API. Must be available offline too with live link to WoRMS when online. Can provide guidance to levels of appropriate levels of taxonomic identification (link to EIP). Methods for querying catalogue using metadata tags (e.g. taxa, location, depth). Expand image library into a catalogue, to include imagery of a range of conditions (image quality, resolution), morphological classifications (CATAMI?), Vulnerable Marine Ecosystems (VMEs), references of abundance, video and stills. Must include metadata for all above and, eventually, multiple examples of each item (under different conditions, camera systems, camera angles). | Project | Benthic imagery library | H | On-going |  |  | DAERA/CEDaR?, Kerry Howell (UoP), MBA/DASSH, Gardline, Emma Sheehan (UoP), SEPA, Jaime Davies (UoP), Envision, Jen Durden (NOC), Seastar Survey Ltd., Cefas, Nicola Foster (UoP) | JNCC, Gardline, Envision, Eastern IFCA, NE? |  |  | Reference collection – accredited set of images to show architype of species A or habitat x etc. Dassh development of the MEDIN Automated Image Management System (MAIMS) (https://www.dassh.ac.uk/maims/). JNCC and DASSH both use Resource Space based solutions (https://www.resourcespace.com/) | BODC? DASSH? JNCC? SEPA - could we use an existing website (e.g.. DASSH, MARLIN, WORMS) instead of creating a new one? Need to review what exists already and why that doesn’t/couldn’t work for the BPG
Data flows | Benthic imagery data archives and catalogues | 68 | Explore options for ownership/management of central/common image library of reference collection and, potentially, other annotated imagery | Ideally should be publicly funded and free (HBDSEG/NMBAQC?) but could have subscription costs if needs be. Must have a sustainable cost model. Need to send out data call for available imagery, offer incentives, assess imagery quality (validation by experts), tag imagery and existing catalogue imagery. Need to identify what’s required/scope of a common image library, then identify priorities and trial it on a data set – test a beta version. | Coordination | Range of options for implementation of Benthic imagery library | M | In progress |  |  | MBA/DASSH, Cefas | JNCC, Eastern IFCA, NE? |  |  | Development has progressed in terms of DASH fulfilling this purpose. The outcome system often is the result of who pays or funds this. FATHOM net (https://fathomnet.org/fathomnet/#/) are struggling with experts to review the images without the funding for quality control. Funding would need to pay for taxonomists and infrastructure, which is challenging.
Data flows | Benthic imagery data archives and catalogues | 69 | Develop confidence assessment approach for image library reference collections | This task ensures the quality of reference imagery is maintained as it is used by the benthic imagery library. | Project | Image library confidence assessments | L | Hasn't started |  |  | MBA/DASSH, Cefas | JNCC, Eastern IFCA, NE?
Data flows | Benthic imagery data archives and catalogues | 70 | Identify knowledge gaps in reference collections and address | Address gaps by feeding them back into imagery acquisition/survey stages of work flows. | Project | Complete reference collections | L | Hasn't started |  |  | MBA/DASSH, NE | Eastern IFCA, Seastar Survey Ltd.
Training and Quality Assurance | Benthic Imagery Action Plan co-ordination | 71 | Explore creation of a ‘Centre of Excellence for Taxonomy’ in the UK | Develop strategies to maintain experience and skill of human observers as machine learning algorithms and annotation software are used more frequently, to include definition of future role of human observers. | Coordination | UK Centre of Excellence for Benthic Taxonomy | M | Hasn't started |  |  |  | Eastern IFCA |  |  |  | SEPA - this whole theme should be lead by NMBAQC because if the BPG organise it then then in theory we are creating something for ourselves that we can pass.
Training and Quality Assurance | Benthic imagery analysis training scheme | 72 | Develop online imagery identification tool of similar quality to Habitas.org | Tool should be an online resource that contains links to all resources, book references, upcoming training courses, online catalogues. A range of imagery must be used for examples of taxa and morphotaxa, e.g. from drop camera video and stills, diver stills, AUV video. | Project | Online identification tool | M | Hasn't started |  | CEDaR NI?, | Kerry Howell (UoP), Gardline, Jaime Davies (UoP), Envision, Cefas, Nicola Foster (UoP) | Gardline, Envision, Eastern IFCA, Seastar Survey Ltd.
Training and Quality Assurance | Benthic Imagery Action Plan co-ordination | 73 | Identify and review training providers across NW Atlantic area and for different levels of taxonomic expertise/taxa groups |  | Coordination | List of training providers | L | Hasn't started |  |  | Kerry Howell (UoP), Jaime Davies (UoP) | Eastern IFCA |  |  |  | The Big Picture Group could collectively create this list
Training and Quality Assurance | Benthic imagery analysis training scheme | 74 | Assess the effect training has on consistency of data and determine its limitations | Important to determine the value of training in this task. Assessment of this value should be determined before training improvements have been made and afterwards to evaluate effectiveness of training and this part of the Action Plan. | Project | Training benefits and limitations report | M | Hasn't started |  |  | Gardline, Jaime Davies (UoP) | Gardline, Eastern IFCA |  |  |  | To be carried out by the Benthic Imagery Training Body (Task 10)
Training and Quality Assurance | Benthic imagery analysis training scheme | 75 | Review imagery analysis training approaches for video and stills and identify training needs across UK, identify gaps and scope out training workshops/courses to meet training needs | Training needs could be identified by questionnaire across Big Picture group. Workshops may be proposed for annotation tools, taxonomy, enumeration methods, video identification, automated annotation, machine learning, different biomes, SACFOR, NMBAQC, generic taxonomy and local/regional taxonomy, emerging taxonomic techniques (i.e. molecular). Evaluate delivery mechanisms for training resources and introductions of new techniques, including for maintenance of training standards over time (i.e. refresher tests), and recommend most appropriate routes. Explore options for central resources: completely public repository in NMBAQC, Conservation Agency, Natural History Museum, MarLIN, Universities) vs restricted access (but no costs) vs licensed access (costs for access). Explore delivery of training via online route vs workshop route (e.g. Field Studies Council, Dale Fort), inhouse vs external training and the levels required of each. | Project | Imagery analysis training needs Training workshops and courses proposals | H | Hasn't started |  |  | Kerry Howell (UoP), Emma Sheehan (UoP), Jaime Davies (UoP), Cefas, Nicola Foster (UoP) | Gardline, Eastern IFCA |  |  |  | To be carried out by the Benthic Imagery Training Body (Task 10)
Training and Quality Assurance | Benthic imagery analysis training scheme | 76 | Collate all existing training materials, guidance and analysis tools and make centrally available as a common resource | Review to discover training tools and resources, followed by collation and then summarise and make available, perhaps via a table of weblinks (similar to the JNCC Marine Monitoring Method Finder13). Must include Habitas.org, Marine Biologists Forum (Facebook). | Project | Imagery training resource hub | H | Hasn't started |  |  | NE | Eastern IFCA, Seastar Survey Ltd. |  |  |  | To be carried out by the Benthic Imagery Training Body (Task 10)
Training and Quality Assurance | Benthic imagery data archives and catalogues | 77 | Create pathways for reference collection imagery, especially from image annotation software, for testing and training purposes | This task will be facilitated by creating a central imagery library of reference collection, from which software can be developed to extract test and training imagery. Note there is another task to create pathways for annotated imagery into machine- learning workflows (Task 57). | Project | Recommendations for best flows of reference collection imagery for use in ring tests and training | M | Hasn't started |  |  |  | Eastern IFCA, Seastar Survey Ltd. |  |  |  | To be carried out by the Benthic Imagery Training Body (Task 10)
Training and Quality Assurance | Benthic imagery analysis training scheme | 78 | Develop new training courses and materials to meet imagery training needs, along with minimum training requirements (for each course), including materials for specific taxa using expert knowledge (e.g. Seasearch guides) and machine learning courses and support for benthic biologists and ecologists | This task aims to develop multiple courses and training materials to meet benthic imagery analysis needs and purposes. Courses could be aimed at beginner (introductory), intermediate and expert levels. Could have different training requirements for different purposes (levels of training). Could have basic inductions with set pass/fail limits to achieve accreditation. Tests could be designed for different levels of skill and taxonomic expertise – generic entry level requirements vs detailed taxa-specific requirements (carried out by experts). Explore delivery options such as webinars and online courses to reduce costs. Strategies to improve general knowledge and understanding of data handling skills, annotation software and machine learning algorithms | Multiple projects | Courses and materials bespoke to training needs identified in the review | H | Hasn't started |  |  | Kerry Howell (UoP), Emma Sheehan (UoP), Jaime Davies (UoP), Envision, PMSL, Cefas, Nicola Foster (UoP) | Envision, Seastar Survey Ltd. |  |  |  | To be carried out by the Benthic Imagery Training Body (Task 10)
Training and Quality Assurance | Quality Assurance Framework for benthic imagery | 79 | Develop standard method for assessing differences between datasets determined by different observers as a part of QA | There are statistical approaches useful for assessing the difference between data annotated by different analysts, including exploration of Lin’s Concordance Correlation Coefficient, or Largo function in BIIGLE14 software. Different approaches should be compared and most reliable, optimum method should be standardised by the NMBAQC. | Project | Observer data assessment tool for QA | H | In progress |  | JNCC | Kerry Howell (UoP), Emma Sheehan (UoP), SEPA, Jaime Davies (UoP), NE, Cefas, Nicola Foster (UoP) | Gardline, Eastern IFCA | Defra | Development of a Epibiota QA system for NMBAQC |  | Should this be led by NMBAQC? SEPA - agree
Training and Quality Assurance | Quality Assurance Framework for benthic imagery | 80 | Assess factors of analyst variability (fatigue/stress/time of day) on imagery and develop recommendations for best practice | A study to investigate factors that contribute to variability of data determined by analysts. Should incorporate existing knowledge on the subject to make recommendations for best practice. | Project | Guidelines for annotation best practice | M | Hasn't started |  |  | Jaime Davies (UoP), Jen Durden (NOC), Nicola Foster (UoP) | Gardline, Eastern IFCA |  |  |  | Should this be led by NMBAQC? SEPA - agree
Training and Quality Assurance | Quality Assurance Framework for benthic imagery | 81 | Evaluate analyst variability for quality control purposes to estimate acceptable levels of error | Develop methods to determine the variability of individual analysts and determine acceptable levels of error for imagery annotation purposes. | Project | Analyst variability assessment tool for ring tests | M | Under consideration |  |  | JNCC, SEPA, Jen Durden (NOC), NE | Gardline, Eastern IFCA |  |  |  | Should this be led by NMBAQC? SEPA - agree
Training and Quality Assurance | Quality Assurance Framework for benthic imagery | 82 | Evaluate habitat variability giving examples of specific habitats and species to estimate acceptable levels of error | Determine the variability of habitats and species in benthic habitats and determine acceptable levels of error for imagery annotation purposes. The Marine Biological Association (MBA) have work in this area to follow up on for this task. | Project | Guidelines on acceptable levels of habitat and species variability | M | Hasn't started |  | Cefas | SEPA, NE | Eastern IFCA |  |  |  | Should this be led by NMBAQC? SEPA - agree
Training and Quality Assurance | Quality Assurance Framework for benthic imagery | 83 | Review of quality assessment approaches for imagery, including ring tests and NMBAQC recommendations for quality control checks | Review current Quality Assurance measures for benthic imagery in the UK to determine successes, overlap and redundancy, include assessment of which organisations follow NMBAQC recommendations. Organisations to update internal and external Quality Control guidelines. | Project | Updated NMBAQC quality control checking guidelines for internal and contracted work | M | Under consideration |  |  | JNCC, Jaime Davies (UoP), Seastar Survey Ltd., NE | Eastern IFCA, Cefas |  |  |  | Should this be led by NMBAQC? SEPA - agree
Training and Quality Assurance | Quality Assessment Tool for benthic imagery | 84 | Develop simple methods to quantify imagery data quality, perhaps using test cards that ask participant which square they can resolve | Explore existing methods for this task, including Nephrops TV survey quality checks. Adopt useful methods for rapid assessment of quality of imagery before annotation. | Project | Image quality assessment tool | M | Hasn't started |  | Cefas | Jaime Davies (UoP), Seastar Survey Ltd., NE, Nicola Foster (UoP) | Eastern IFCA |  |  |  | Should this be led by NMBAQC? SEPA - agree
Training and Quality Assurance | Quality Assurance Framework for benthic imagery | 85 | Identify and develop a range of quality assurance measures (competency tests?) for different imaging purposes | May involve development of competency tests for certain groups of taxa, morpho-groups, indicators, biotopes, enumeration methods and regions to ensure appropriate standards are met for each imagery purpose. Methods may be developed to evaluate observer variability. Consider frequency of tests (annual) and potential for ‘accreditation’ – minimum competency for different standards. | Multiple projects | Quality assurance measures/competency tests required to meet all standard purposes | M | In progress |  | JNCC | Jaime Davies (UoP), NE | SEPA, Eastern IFCA, Cefas | Defra | Development of a Epibiota QA system for NMBAQC |  | Should this be led by NMBAQC? SEPA - agree
Training and Quality Assurance | Benthic imagery analysis training scheme | 86 | Create training standards/accreditation scheme | This task brings together many other tasks as it requires an understanding of financial incentives for accreditation, possible endorsement funding models, standard setting and numerous training resources. Could link this scheme to the Field Studies Council (FSC) or NMBAQC. Could be endorsed by Chartered Institute of Ecology and Environmental Management (CIEEM) or Institute of Environmental Sciences (IES). Useful to review Marine Stewardship Council (MSC) accreditation schemes for this task. | Project | Training standards/accreditation scheme | M | Hasn't started |  |  | Kerry Howell (UoP), Emma Sheehan (UoP), Jaime Davies (UoP), Nicola Foster (UoP) | JNCC, Gardline, SEPA, Envision, Eastern IFCA, Cefas | Defra | Development of a Epibiota QA system for NMBAQC |  | Should this be led by NMBAQC? SEPA - agree
Training and Quality Assurance | Benthic imagery analysis training scheme | 87 | Development of an online training module system | System must be accessible and easy to use/good interface. For example, Marine Stewardship Council audit training systems. System could also have online practice tests for refreshers. | Project | Imagery training resource hub: live training module system | L | Hasn't started |  |  | NS | Gardline, Eastern IFCA |  |  | NS have developed online training materials for citizen science/monitoring | Should this be led by NMBAQC? SEPA - agree
Note on I66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work through other relevant workshops and groups by GD on archival approaches and format for jpeg and specifically video.
Note on I68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Beginnings of "default" option through DASSH's MAIMS image catalogue system for recommended routes. Some further open sharing work thorugh investigations into IIIF and org's own image catalogue systems.
Note on I69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Work continuing by Kerry Howell on SmartarID pilot in the deepsea. Taking the reference aspect but not necessarily classification system aspect. (i.e. aspects of data model and site, rather than anything else) Seek workshop feedback on alternative systems or proceed with recommending and developing on top of SmartarID (to fulfil additional user-stories, etc). Reply: Also included governance questions of "What is a trustworthy reference list?". Should really have some oversight and governance here, or is it just a free for all?
Note on I70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Heavily reliant on 67 as a dependency as it stands. However, would suggest a split between ref catalogue and general catalogue, and reword accordingly. Need to do a full discovery workshop here, we could go "Full Fathomnet" (and accept the costs...) or something lighter.
Note on I71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Suggest moving this to another working group - this is not a catalogue/archive matter. Possibly Training/Quality Assurance?
Note on I72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dependency on 67 being at least part completed....

## Big_Picture_Group
List of organisations involved in Big Picture Group:
Type of organisation | Organisation
Statutory Nature Conservation Bodies for the UK (note DAERA is also a devolved government department in Northern Ireland) | Joint Nature Conservation Committee (JNCC)
Natural Resources Wales (NRW)
Natural England (NE)
Marine and Fisheries Division, Department of Agriculture, Environment and Rural Affairs (DAERA)
NatureScot (NS)
Government- and research council-funded research institutes | Agri-Food Biosciences Institute (AFBI)
Biofar (Faroe Islands)
Centre for Environment, Fisheries and Aquaculture Science (CEFAS)
Marine Scotland Science (MSS)
Government-funded environmental protection agencies and fisheries authorities | Eastern Inshore Fisheries and Conservation Authority (IFCA)
Environment Agency (EA)
Scottish Environment Protection Agency (SEPA)
Independent marine research institutes | Marine Biological Association of the UK (MBA)
Scottish Association for Marine Science (SAMS)
Wageningen Marine Research (Netherlands)
National Oceanography Centre (NOC)
Universities with academic researchers working in various fields of marine benthic imagery analysis | Heriot-Watt University
University of East Anglia
University of Edinburgh
University of Plymouth
University of Oxford
University of Southampton
University of Ulster
Environmental consultancies (organisations and independents) | APEM
Aquatic Survey and Monitoring Limited (ASML)
Bureau Waardenburg BV (Netherlands)
Cloudbase Productions
Crangon Limited
Ecospan Environmental Limited
Envision Mapping Limited
Fugro GB Marine Limited
Gardline
Marine EcoSol
Precision Marine Survey Limited (PMSL)
Ocean Ecology Limited
Seastar Survey Limited
Hardware developer | SubCImaging
Government departments | Department of Agriculture, Environment and Rural Affairs (DAERA)
Department of Environmental, Farming and Rural Affairs (DEFRA)
Marine Scotland (MS)
Government funded working groups | MEDIN